## Timeline
Comparison of Machine Learning with Deep Learning Models for Flight Price Prediction
Nama Kelompok : Kelompok 2
| Project Start Date |  | 2024-06-03 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Projecyt Manager |  | 2024-06-21 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22
 | time axis 2024-06-03 to 2024-07-28
WBS | TASK | Deliverable | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-06-03 to 2024-07-28
1 | Business Analis |  |  |  |  | - |  |  | -
1.1 | Mencari Dataset | Dataset | Celerates |  | 2024-06-03 | 2024-06-03 | 1 | 100% | 1
1.2 | Menentukan Dataset | Dataset | All |  | 2024-06-04 | 2024-06-04 | 1 | 100% | 1
1.3 | Menentukan Problem | Problem | All |  | 2024-06-04 | 2024-06-04 | 1 | 100%
1.4 | Menentukan dan mencari Judul | Judul | All |  | 2024-06-04 | 2024-06-04 | 1 | 100%
2 | Data Modeler |  |  |  |  | - |  |  | -
2.1 | Bussines Understading, Data prepartion | Problem dan preparation data | All |  | 2024-06-05 | 2024-06-05 | 1 | 100% | 1
2.2 | Pemodelan | Hasil model | All |  | 2024-06-05 | 2024-06-06 | 2 | 100%
2.3 | Evaluasi Model | Menentukan model yang pas dan cocok | All |  | 2024-06-06 | 2024-06-06 | 1 | 100% | 1
2.4 | Revisi model | Perbaikan model | All |  | 2024-06-07 | 2024-06-10 | 4 | 100% | 2
3 | Data Visualisation |  |  |  |  | - |  |  | -
3.1 | Visualiasasi model | Tampilan visualiasi | All |  | 2024-06-11 | 2024-06-12 | 2 | 100% | 2
3.2 | Revisi Visualisasi | Hasil Revisi |  |  | 2024-06-13 | 2024-06-13 | 1 | 100% | 1
3.3 | Dashboard Tableau | Tampilan Dashboard |  |  | 2024-06-13 | 2024-06-13 | 1 | 100% | 1
4 | Laporan Akhir |  |  |  |  | - |  |  | -
4.1 | Penyusunan Point laporan Akhir | Penyusunan Point | All |  | 2024-06-13 | 2024-06-14 | 2 | 100% | 2
5 | Technical Desain
5.1 | PPT | Desain PPT | All |  | 2024-06-15 | 2024-06-15 | 1 | 100%
6 | Video Presentasi | bar: 2024-06-03 to 2024-07-13
6.1 | Record Video | Video Presentasi + Up Youtube | All |  | 2024-06-18 | 2024-06-18 | 1 | 100%

## Copy of Timeline
Comparison of Machine Learning with Deep Learning Models for Flight Price Prediction
Nama Kelompok : Kelompok 2
| Project Start Date |  | 2024-06-03 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Projecyt Manager |  | 2024-06-21 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10 | [6 empty] | 2024-06-17 | [6 empty] | 2024-06-24 | [6 empty] | 2024-07-01 | [6 empty] | 2024-07-08 | [6 empty] | 2024-07-15 | [6 empty] | 2024-07-22
 | time axis 2024-06-03 to 2024-07-28
WBS | TASK | Deliverable | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-06-03 to 2024-07-28
1 | Business Analis |  |  |  |  | - |  |  | -
1.1 | Mencari Dataset | Dataset | Celerates |  | 2024-06-03 | 2024-06-03 | 1 | 100% | 1 | bar: 2024-06-03
1.2 | Menentukan Dataset | Dataset | All |  | 2024-06-04 | 2024-06-04 | 1 | 100% | 1 | bar: 2024-06-04
1.3 | Menentukan Problem | Problem | All |  | 2024-06-04 | 2024-06-04 | 1 | 100%
1.4 | Menentukan dan mencari Judul | Judul | All |  | 2024-06-04 | 2024-06-04 | 1 | 100%
2 | Data Modeler |  |  |  |  | - |  |  | -
2.1 | Bussines Understading, Data prepartion | Problem dan preparation data | All |  | 2024-06-05 | 2024-06-05 | 1 | 100% | 1
2.2 | Pemodelan | Hasil model | All |  | 2024-06-05 | 2024-06-06 | 2 | 100%
2.3 | Evaluasi Model | Menentukan model yang pas dan cocok | All |  | 2024-06-06 | 2024-06-06 | 1 | 100% | 1
2.4 | Revisi model | Perbaikan model | All |  | 2024-06-07 | 2024-06-10 | 4 | 100% | 2 | bar: 2024-06-07 to 2024-06-10
3 | Data Visualisation |  |  |  |  | - |  |  | -
3.1 | Visualiasasi model | Tampilan visualiasi | All |  | 2024-06-11 | 2024-06-12 | 2 | 100% | 2
3.2 | Revisi Visualisasi | Hasil Revisi |  |  | 2024-06-13 | 2024-06-13 | 0 | 0% | 1
3.3 | Dashboard Tableau | Tampilan Dashboard |  |  | 2024-06-13 | 2024-06-13 | 0 | 0% | 1
4 | Laporan Akhir |  |  |  |  | - |  |  | -
4.1 | Penyusunan Point laporan Akhir | Penyusunan Point | All |  | 2024-06-04 | 2024-06-13 | 10 | 100% | 8
5 | Technical Desain
5.1 | PPT | Desain PPT | All |  | 2024-06-14 | 2024-06-14 | 1 | 100%
6 | Video Presentasi
6.1 | Record Video | Video Presentasi + Up Youtube | All |  | 2024-06-18 | 2024-06-18 | 1 | 0%